## START HERE
POLARIS FINALIZED V1 PROCUREMENT SPECIFICATION
Answer | Not every previous purchase was required. Separate installed components from spare quantities, optional modules and included accessories. This workbook supersedes the earlier 38-line budget as the procurement specification.
Scope | Core = motorized qualitative polarization imaging of a clear polycarbonate specimen. Existing circuit retained: Arduino + A4988 + motor + home switch + LED MOSFET + USB camera. HX711/load cell remains optional.
What final means | Circuit functions and installed electrical counts are audited. Camera model, ring/support dimensions, belt length and optical layout remain explicitly HOLD/VERIFY items. Do not order them blindly.
No guarantee yet | Hardware has not been assembled/bench-tested. Firmware/acquisition integration, alignment and calibration remain. Purchasing this list alone does not establish calibrated stress measurement or trained AI.
Google Sheets | Upload this XLSX to Google Drive, open with Google Sheets and use File > Save as Google Sheets if it remains in Office-editing mode. Or use Sheets > File > Import > Upload > Create new spreadsheet. This is an importable workbook, not an already-created Google Sheet.
Read tabs | Core BOM = installed requirements; Optional = extras/modules; Changes = reconciliation; Connections = circuit map; Purchase gates = unresolved decisions; Supplier searches = unverified searches; Quotes = enter actual prices.
Pricing | Live prices and seller reliability have NOT been verified. Previous INR 15,000 was a hypothetical allowance. Quotes remain INCOMPLETE until all order quantities/prices, tax and shipping are supplied.
Computer required | Reuse a laptop with two adequate USB data connections (or suitable powered hub if needed); camera processing runs on laptop, not Uno. Laptop purchase excluded.
Lab tools required | Access to multimeter, soldering/assembly tools and caliper/micrometer is needed. Borrow/use lab stock; these are tools, not installed parts.
Loaded tests | The core includes a non-loading specimen holder. To investigate controlled applied stress, separately provide a rated loading fixture and suitable force measurement; the motor only rotates P2.
Optical stock | Two polarizer FUNCTIONS are mandatory. Two retail 150 x 150 sheets are not always necessary; confirm cut layout. Do not replace linear film with photographic CPL.
Added missing supports | Specimen holder, backlight support, home-switch bracket/actuator, driver headers/sockets, and belt-tension adjustment are now explicit. Bundle fabrication where practical.
Date | 18 October 2026; based on existing pictorial circuit and software-only hardware status.
Existing diagram | https://github.com/Aemili09/POLARIS/blob/main/hardware/POLARIS_Pictorial_Wiring.png

## Core BOM
ID | Component | Installed quantity | Installed unit | Purchase quantity / bundle rule | Specification | Order status | Circuit function | Compatibility / qualification
B01 | Arduino Uno R3 ATmega328P | 1 | board | 1 board; use existing if available | 5 V logic; 16 MHz; Uno pin layout; USB data interface | SPEC READY | U1; D2/D3/D4/D7/D9 control; D5/D6 reserved for optional HX711 | Confirm actual USB socket and USB driver; USB powered, Vin/barrel unused.
B02 | A4988 carrier with heatsink | 1 | driver assembly | 1 set; do not separately buy an included heatsink | STEP/DIR; adjustable current limit; 1/16 microsteps; documented pinout and Rs | SPEC READY | U2; motor power stage | Current-sense resistor value must be known. 0.60 A initial setting needs actual torque/temperature test. Carrier header pins may be loose or absent; see B35.
B03 | NEMA17 4-wire bipolar stepper; 17HS4401 candidate | 1 | motor | 1 motor | 200 full steps/rev (1.8 degrees); 4 wire; phase rating >=0.60 A; 5 mm shaft for selected pulley | VERIFY DATASHEET | M1; rotates analyzer, not specimen loading | 17HS4401 listings vary. Confirm shaft, phase current, dimensions and winding pairs; do not assume identical specifications from model name.
B04 | UVC USB camera; Logitech C270 candidate only | 1 | camera | 1 AFTER camera-control and field-of-view check | Lockable exposure, gain and white balance; stable focus; usable working distance/field of view; supported laptop software | HOLD: COMPATIBILITY | CAM1 -> laptop USB, never Uno GPIO | C270 is not a guaranteed measurement-camera selection. Confirm disabling automatic processing on intended OS, focus on specimen, and visibility through analyzer opening. Buy another documented UVC camera if it fails.
B05 | Isolated regulated 12 V DC / 3 A enclosed adapter | 1 | adapter | 1 | Reputable supply; adequate protection; declared connector/polarity; no exposed mains terminals | SPEC READY | PS1; external motor and LED supply | Match B30 socket. Logic still comes from Uno USB. 3 A is adapter capacity, not guaranteed circuit draw.
B06 | FQP30N06L logic-level N-channel MOSFET | 1 | MOSFET | 1; a second is an optional spare | TO-220; manufacturer-documented G/D/S; specified operation with 5 V gate drive | SPEC READY | Q1; low-side LED switching | Front marked face: 1 gate, 2 drain/tab, 3 source for selected device. Do not substitute a non-logic-level MOSFET blindly.
B07 | SPDT lever microswitch; Omron SS-5GL candidate | 1 | switch | 1; a second is an optional spare | COM/NC/NO; compatible lever travel and mounting; documented terminals | VERIFY MOUNT | SW2; NC home switch to D7 | Use COM and NC. B16 provides adjustable mount and moving-ring actuator. Mechanical home is not calibrated optical zero.
B08 | Visible linear polarizing film (P1 and P2) | 2 | optical pieces | Start with 1 CUTTABLE 150 x 150 mm sheet only if both blanks fit; otherwise 2 sheets | Non-adhesive visible LINEAR film; not photographic CPL; request transmission/extinction specs | HOLD: CUT LAYOUT | P1 fixed input + P2 rotating analyzer | Two filters are required, not necessarily two retail sheets. Illustrative layout: 110 x 60 mm P1 blank plus <=50 mm P2 blank fits one 150 x 150 mm sheet. Confirm holder margins, clear aperture and vignetting before cutting or buying.
B09 | 12 V diffused white LED backlight panel | 1 | panel | 1 integrated panel with current limiting and diffuser | Illuminated area >=100 x 50 mm for initial view; <=0.5 A at 12 V; documented integrated current limiting | VERIFY LISTING | L1; + to switched 12 V, - to Q1 drain | Default selection includes diffuser. If absent, add O01; if no internal current limiting, this selection is not electrically compatible without a correctly designed LED driver.
B10 | Fixed P1 polarizer frame | 1 | holder | 1 fabricated frame or existing equivalent | Holds selected film flat; adjustable orientation; clear aperture covers illuminated specimen region | FABRICATE | Supports P1 | Can be fabricated with base supports; do not pay twice if bundled into assembly.
B11 | Custom 80T GT2 annular analyzer ring AND P2 holder | 1 | ring/holder assembly | 1 combined assembly; no second rotating filter holder | 2 mm pitch; tooth profile matches belt; 6 mm belt; optical opening; film retention; bearing interface | HOLD: DRAWING | Driven 80T ring; P2 mounting | NOT a standard solid pulley. 80T x 2 mm pitch gives ~50.9 mm pitch diameter; usable clear aperture is smaller. Size aperture with camera optical cone; include ring balance and retention.
B12 | GT2 closed-loop timing belt | 1 | belt | 1 AFTER centre distance and tension travel are fixed | 2 mm pitch, 6 mm width, matching tooth profile; length from mechanical drawing | HOLD: LENGTH | Connects 20T motor pulley to 80T ring | Do not guess belt length. Slotted motor mount or another specified adjustment must provide tension control.
B13 | GT2 20T motor pulley | 1 | pulley | 1 with grub screws | 2 mm pitch; 6 mm belt; 5 mm shaft bore if B03 verified as 5 mm | VERIFY SHAFT | 20T drive; 4:1 reduction with B11 | Same belt/tooth profile as B11/B12. Match actual shaft and provide secure retention.
B14 | Bearing / roller support for analyzer ring | 1 | support assembly | 1 assembly AFTER drawing; individual bearing quantity from drawing | Allows clear optical aperture; constrains ring axially/radially; compatible with B11 | HOLD: DRAWING | Supports rotating P2 independently of motor | Exact bearing size/quantity cannot be finalized without the ring drawing. Do not buy an arbitrary shaft bearing that blocks the camera view.
B15 | NEMA17 adjustable mounting bracket | 1 | bracket | 1 bracket; integrate adjustment into bracket or base | NEMA17 pattern; suitable screw depth; slotted adjustment for belt tension | VERIFY LAYOUT | Motor mount and belt tension adjustment | If bracket is not slotted, provide slots in base. No extra idler is mandated when sufficient adjustment is built in.
B16 | Home-switch bracket and ring actuator/cam | 1 | paired mechanical set | 1 set, integrated with ring/base where possible | Adjustable switch position; reliable press/release; clearance during rotation | FABRICATE | Makes SW2 physically actuate at home | Missing from earlier shopping list. Include cam/flag in B11 fabrication quote where possible; do not double-charge the integrated feature.
B17 | Rigid adjustable camera mount | 1 | mount | 1 matched to chosen camera | Locks viewing direction/working distance; compatible with actual camera body | VERIFY CAMERA | Camera support | C270 does not automatically provide a standard tripod socket. Confirm mount interface before purchase.
B18 | Specimen holder with two gentle edge supports | 1 | holder assembly | 1 non-loading holder | Maintains specimen position; unobstructed viewing region; avoids unintended bending/clamping stress | FABRICATE | Holds sample between P1 and P2 | Missing from earlier list. NOT a tensile loading fixture. Hold outside viewed region; document mounting-induced baseline changes.
B19 | Backlight/diffuser support | 1 | mount | 1; omit separate purchase if panel/base kit includes it | Rigid support for B09; adjustable position/alignment | FABRICATE / BUNDLE | Holds source before P1 | Missing as an explicit item previously. Can share fabricated rail/base with other fixed mounts.
B20 | Rigid optical base / rail | 1 | base assembly | 1 AFTER working-distance layout | Rigid board or metal base; feet/support; dimensions based on optics and camera focus | HOLD: LAYOUT | Mechanical reference for entire setup | Earlier 300 x 200 mm was illustrative, not finalized. Allow actual camera working distance, specimen and belt clearances.
B21 | M3/M4 fasteners, washers, standoffs | 1 | assembly kit | 1 kit; exact lengths/count after drawings | Match motor, base, mounts, bearing supports and circuit-board mounting | VERIFY LAYOUT | Secures electronics and optics | One integrated fastener kit, not separate unexplained kits for each holder.
B22 | 10 kΩ 1/4 W 1% metal-film resistor | 4 | resistors | 4 installed; buy minimum pack; rest are spares | 10 kΩ, axial, 0.25 W, 1% | SPEC READY | R1 ENABLE pull-up; R2 STEP pull-down; R3 DIR pull-down; R6 MOSFET gate pull-down | Earlier quantity 10 included 6 extras. All four functions remain in the current circuit.
B23 | 4.7 kΩ 1/4 W 1% metal-film resistor | 1 | resistor | 1 installed; buy minimum pack | 4.7 kΩ, axial, 0.25 W, 1% | SPEC READY | R4; D7 HOME pull-up | Earlier quantity 5 included 4 extras.
B24 | 100 Ω 1/4 W 1% metal-film resistor | 1 | resistor | 1 installed; buy minimum pack | 100 Ω, axial, 0.25 W, 1% | SPEC READY | R5; D9 to Q1 gate series resistor | Earlier quantity 5 included 4 extras.
B25 | 100 µF 35 V radial electrolytic capacitor | 1 | capacitor | 1 installed; spare optional | 100 µF, 35 V, radial, preferably 105°C | SPEC READY | C1; VMOT to common GND | Positive to VMOT, negative to GND; physically close to A4988. Earlier quantity 2 included a spare.
B26 | 100 nF / 0.1 µF 50 V X7R ceramic capacitor | 2 | capacitors | 2 installed; buy minimum pack | 100 nF, 50 V, X7R, leaded for perfboard | SPEC READY | C2 A4988 VDD bypass; C3 HOME filter | Earlier quantity 5 included 3 extras. Keep both circuit functions.
B27 | SPST DC power switch | 1 | switch | 1 | Documented rating >=3 A at 12 V DC | SPEC READY | SW1; external motor/LED supply switch | Not interchangeable with home microswitch SW2. Cutting this switch does not remove Uno USB power.
B28 | Inline fuse holder | 1 | holder | 1 | Matches fuse dimensions; suitable current/DC voltage rating; insulated | VERIFY FUSE | F1 holder | Keep holder and fuse physically compatible.
B29 | 2 A fuse | 1 | fuse installed | 1 installed; spare fuses optional | Adequate DC rating; selected format and time characteristic | VERIFY INRUSH | F1; external power protection | 2 A is provisional circuit choice; verify startup demand and wire protection during bench testing. Earlier 3 were 1 installed + 2 spares.
B30 | Female DC barrel jack to screw terminal | 1 | power connector | 1 only if adapter lead requires it | Matches B05 connector; typically 5.5 x 2.1 mm centre-positive, but verify | CONDITIONAL PURCHASE | PS1 adapter connection | Do not buy if equivalent suitable connector is already included in power assembly.
B31 | 2-position screw terminal blocks | 5 | blocks in proposed perfboard layout | 5 if using this termination plan; existing equivalent may replace them | >=3 A; conductor-compatible; 5.08 mm pitch works with 2.54 mm perfboard spacing | LAYOUT CHOICE | DC input pair; LED pair; motor coil A pair; motor coil B pair; logic supply pair | Five is a specified implementation allowance, not an IC requirement. Count may change if using different connectors; do not buy both complete connector schemes.
B32 | Signal wiring / Arduino jumper pigtail harness | 1 | harness kit | 1 combined kit, not two mandatory separate kits | 24-26 AWG signal wire plus compatible male/female jumper ends as needed | SPEC READY | Uno-to-driver/home/gate signals and 5 V distribution | Earlier hookup-wire and jumper sets overlapped. Include usable connections to Uno headers; no high-current motor/LED path through flimsy jumpers.
B33 | Power wiring | 1 | wire assortment | A few metres; cut lengths after layout | 20-22 AWG stranded for short runs; insulation/rating appropriate; correct terminations | SPEC READY | Adapter, driver VMOT, motor and LED current paths | Route high-current returns directly to supply ground; join logic reference without passing load current through Uno.
B34 | Solderable perfboard | 1 | board assembly | 1 suitably sized board; second only if layout demands it | Supports driver sockets, resistors, capacitors and terminals with insulation/clearance | VERIFY LAYOUT | Interconnect assembly | Earlier 2 were an allowance, not an established requirement. Secure board on standoffs; mount C1 close to driver.
B35 | A4988 carrier pin headers and mating sockets | 1 | connector set | 2 x 8-pin female socket strips; add 2 x 8-pin male headers only if carrier lacks them | 2.54 mm pitch; actual carrier compatible; soldered securely | CHECK BUNDLE | Connects driver carrier to perfboard | Previously missing/implicit. Not a breadboard purchase. Verify header length and spacing before assembly.
B36 | Heat-shrink insulation and cable restraints | 1 | small assortment | 1 assortment or available lab stock | Sizes matched to joints; cable ties/strain relief where needed | SPEC READY | Insulates connections and secures cables | Existing supplies are sufficient; no need for multiple large kits.
B37 | Uno USB DATA cable | 1 | cable in use | 0 if included/owned; otherwise 1 | Matches board USB port; standard Uno R3 normally USB-B; laptop-compatible other end | CHECK BUNDLE | Laptop -> Uno USB power/data | Do not buy a charging-only cable. Camera normally has its own USB lead; do not add a duplicate camera cable without need.
B38 | Clear uncoloured solid polycarbonate coupon | 1 | specimen minimum | 1 minimum; additional independent specimens for later tests | Nominal 200 x 40 x 5 mm; clear uncoated surface; measure actual thickness | VERIFY MATERIAL | Specimen for initial optical acquisition | One initial material is sufficient. PMMA is optional, not required simultaneously. Initial inspection can examine existing residual patterns; no-load holder does not provide controlled applied stress.

## Optional and spares
ID | Item | Classification | Quantity / timing | Why / condition
O01 | Separate opal diffuser | CONDITIONAL | 1 only if B09 lacks effective diffusion | Place before P1. Integrated diffused panel is the default; do not buy twice.
O02 | Clear PMMA / acrylic comparison coupon | OPTIONAL LATER | 0 for initial build | Second material is not required to make the system operate. Separate material calibration if later added.
O03 | Extra MOSFET / home switch / bulk capacitor | OPTIONAL SPARES | 0 extras required | One of each is installed. Spares are useful but not part of minimum circuit.
O04 | Extra resistors / ceramic capacitors / fuses | OPTIONAL SPARES / PACK EXCESS | Only minimum pack excess | Installed counts: 10k x4; 4.7k x1; 100Ω x1; 100nF x2; 100µF x1; fuse x1.
O05 | Matte-black light shield / enclosure | RECOMMENDED | 1 if ambient illumination is not well controlled | Strongly useful for repeatable acquisition but not an electrical circuit component. Use existing controlled enclosure if available.
O06 | Powered USB hub / USB-C adapters | CONDITIONAL | Only if laptop connections/power require it | Need simultaneous camera and Uno data connections; check bandwidth and USB power, not just socket count.
O07 | HX711 module + full-bridge load cell | OPTIONAL MODULE | 0 for core build | Shown as optional in existing circuit. Add together when recording applied force; DT D5, SCK D6, VCC 5 V and GND; bridge E±/A± matched to datasheet.
O08 | Rated loading frame / grips / load-cell mounting | REQUIRED FOR CONTROLLED APPLIED-LOAD TESTS | Not part of qualitative acquisition core | Use a suitable laboratory frame if available. A specimen holder alone cannot apply known tensile force; adding only a load cell does not make a loading system.
O09 | Encoder / closed-loop motion sensing | OPTIONAL FUTURE | 0 initially | Homing plus step counting is the current design; encoder would require additional design and firmware.
O10 | Laser / quarter-wave plates / spectral LEDs | NOT IN CURRENT V1 | 0 | These are future optical variants; adding them changes calibration/model requirements.
O11 | Second rotating analyzer holder | DUPLICATE — DO NOT BUY | 0 | Already included in B11 annular ring assembly.
O12 | Large solderless breadboard | OPTIONAL BENCH TOOL | 0 required for final circuit | Perfboard implementation is selected; breadboard must not substitute for suitable high-current connections.
O13 | Separate LED constant-current driver | NOT NEEDED WITH SPECIFIED PANEL | 0 if B09 includes current limiting | If using a bare LED, this becomes a redesign requirement. Do not operate a bare power LED from 12 V directly.

## Changes vs previous list
Old row | Previous item | Old suggested quantity | New ID | Decision / reason
1 | Uno R3 compatible ATmega328P, 5V, 16MHz | 1 | B01 | Keep one.
2 | A4988 carrier with heatsink | 1 | B02 | Keep one set; count heatsink once.
3 | 17HS4401 NEMA17 bipolar, 1.8 degree, 4 wire | 1 | B03 | Keep one; verify actual motor datasheet.
4 | Logitech C270 HD USB webcam 720p | 1 | B04 | Candidate only: camera controls and optics are a purchase gate.
5 | Isolated regulated 12V DC 3A enclosed adapter | 1 | B05 | Keep one.
6 | FQP30N06L logic-level N-MOSFET TO-220 | 2 | B06 | Reduce 2 to 1 installed; spare optional.
7 | Omron SS-5GL SPDT lever microswitch | 2 | B07 | Reduce 2 to 1 installed; spare optional.
8 | Visible linear polarizing film 150 x 150 mm non-adhesive | 2 | B08 | Need 2 optical pieces, potentially cut from 1 sheet; verify cut layout.
9 | 12V white LED backlight panel >=100 x 50 mm, <=0.5A | 1 | B09 | Keep one, require current-limited diffused panel.
10 | Opal acrylic diffuser approximately 150 x 100 x 1-2 mm | 1 | O01 | Only buy separate diffuser if panel does not include adequate diffusion.
11 | Fixed polarizing-film holder | 1 | B10 | Keep fixed holder.
12 | Adjustable webcam mount compatible with C270 | 1 | B17 | Keep mount; must match chosen camera.
13 | Matte black enclosure panels / foam board | 1 | O05 | Recommended ambient-light control; not a mandatory separate purchase if provided by lab.
14 | GT2 20T pulley 2mm pitch, 5mm bore, 6mm belt width | 1 | B13 | Keep 20T pulley; verify bore/profile.
15 | CUSTOM GT2 80T annular analyzer pulley / holder | 1 | B11 | Keep single combined ring AND rotating holder, fabrication pending.
16 | GT2 closed-loop belt 2mm pitch 6mm wide | 1 | B12 | Keep belt but do not order unknown length.
17 | Analyzer bearing / roller support assembly | 1 | B14 | Keep support assembly; do not guess bearing size.
18 | NEMA17 L mounting bracket | 1 | B15 | Keep adjustable motor mount; include belt tension provision.
19 | Rigid base plate approximately 300 x 200 mm | 1 | B20 | Keep base; dimensions depend on camera/mechanics layout.
20 | M3/M4 screws nuts washers spacers assortment | 1 | B21 | Keep one coordinated hardware kit; dimensions/count from drawing.
21 | 10 kohm 1/4W 1% metal-film resistor | 10 | B22 | Reduce 10 to 4 installed.
22 | 4.7 kohm 1/4W 1% metal-film resistor | 5 | B23 | Reduce 5 to 1 installed.
23 | 100 ohm 1/4W 1% metal-film resistor | 5 | B24 | Reduce 5 to 1 installed.
24 | 100uF 35V radial electrolytic capacitor 105C | 2 | B25 | Reduce 2 to 1 installed.
25 | 100nF 50V X7R ceramic capacitor | 5 | B26 | Reduce 5 to 2 installed.
26 | SPST power switch rated >=3A at 12V DC | 1 | B27 | Keep one external power switch.
27 | Inline fuse holder | 1 | B28 | Keep one matching fuse holder.
28 | 2A fuse with suitable DC voltage rating | 3 | B29 | Reduce 3 to 1 installed; reserve fuses optional.
29 | 5.5 x 2.1mm female DC jack to screw terminal | 1 | B30 | Buy only if connector is not already included.
30 | 2-position screw terminal blocks >=3A | 5 | B31 | Five blocks is selected termination layout, not universal minimum.
31 | 24-26 AWG signal hookup wire assortment | 1 | B32 | Consolidate with jumper pigtails into one signal harness.
32 | 20-22 AWG stranded power wire assortment | 1 | B33 | Keep suitable power wires separately.
33 | Male-male and male-female jumper wire set | 1 | B32 | Consolidate with signal wire; not an additional compulsory duplicate kit.
34 | Solderable perfboard | 2 | B34 | One board initially; second only if layout requires it.
35 | Heat-shrink tubing assortment | 1 | B36 | Keep insulation/restraints; existing stock can be used.
36 | USB-A to USB-B Arduino cable | 1 | B37 | One cable in use; purchase zero if included/owned.
37 | Clear solid polycarbonate 5mm sheet, 200 x 40mm coupons | 1 | B38 | Use one polycarbonate specimen type initially; quantity grows with experiments.
38 | Clear cast PMMA acrylic 5mm sheet, 200 x 40mm coupons | 1 | O02 | PMMA is optional; remove from mandatory initial total.

## Connections
Source / terminal | Destination | Detail | BOM IDs
Uno USB | Laptop USB data port | USB powers Uno; Vin/barrel unused | B01,B37
Camera USB | Laptop second data connection | Not Uno GPIO; fix exposure/gain/WB | B04
D2 | A4988 STEP | R2 10k to GND | B01,B02,B22
D3 | A4988 DIR | R3 10k to GND | B01,B02,B22
D4 | A4988 ENABLE | Active low; R1 10k to +5 V; boot disabled | B01,B02,B22
D7 | Home switch NC | COM to GND; R4 4.7k to +5 V; C3 100nF to GND | B07,B16,B23,B26
D9 | R5 100Ω -> Q1 gate | R6 10k gate to GND | B06,B22,B24
Q1 source pin 3 | Common GND | FQP30N06L marked-face convention; verify datasheet | B06
Q1 drain pin 2/tab | LED negative | LED positive to switched +12 V | B06,B09
Uno 5V | A4988 VDD, MS1/MS2/MS3, RESET, SLEEP, pull-ups | C2 100nF VDD-GND; all mode pins high = 1/16 | B01,B02,B22,B23,B26
Adapter positive | F1 -> SW1 -> switched +12 V | A4988 VMOT and LED positive; NOT Uno 5V | B05,B27,B28,B29,B30
Adapter negative | Common GND | Both A4988 GND pins; Uno GND; Q1 source; switch COM; returns routed appropriately | B01,B02,B05,B06,B07,B33
C1 100µF | Positive VMOT; negative GND | Close to motor driver; 35 V rating | B25
A4988 1A / 1B | One motor winding | Identify pairs by meter with power OFF | B02,B03
A4988 2A / 2B | Other motor winding | Never swap leads while powered | B02,B03
20T -> belt -> 80T ring | P2 analyzer rotates on independent support | 4:1; 12,800 microstep commands/rev at 200 motor steps and 1/16 | B03,B11,B12,B13,B14,B15
Optical order | LED/diffuser -> P1 -> specimen -> P2 -> camera | P1 fixed; P2 rotates; holder must not obstruct light | B04,B08,B09,B10,B11,B17,B18,B19
D5 / D6 | Unused in core; HX711 DT / SCK if module added | Optional module requires separate mechanical loading design | O07,O08

## Purchase gates
Gate | Check | When | Acceptance requirement
G01 | Camera model / controls / optics | Before camera purchase | Verify actual OS can lock exposure/gain/WB, focus covers specimen working distance and full viewing area passes through proposed analyzer aperture. C270 is only a candidate.
G02 | Ring and support drawing | Before B11/B14 fabrication | Specify aperture, tooth profile, bearing/roller geometry, axial restraint, film retention, mount and switch actuator. Check that no bearing blocks the optical path.
G03 | Belt and base dimensions | Before B12/B20 order | Choose centre distance and tension adjustment, then belt length; allow working distance. 300 x 200 mm is not a validated base size.
G04 | Polarizer cut layout | Before B08 order/cut | Two usable filters must fit selected material sheet including clamping margins. One retail sheet is enough only if both footprints fit.
G05 | Power and bundle compatibility | Before electrical order | Confirm adapter/socket polarity, LED internal current limiting, driver Rs, carrier headers, heatsink and USB data cable inclusion.
G06 | Electrical bench check | Before motor/LED operation | Inspect polarity/continuity; set current limit from actual Rs; check no 12 V to logic; test supply and switching, then temperature and motor torque. Proposed circuit is not bench validated.
G07 | Homing / capture firmware | Before automated acquisition | Implement boot disabled, timeout, debounce, switch-release validation, optical zero, move-complete acknowledgement, settling and fresh-frame capture. Wiring alone does not provide this software.
G08 | Optical repeatability / calibration | Before measurement claims | Empty-path sweep, dark/flat checks, fixed camera controls, remount repeats and known specimen thickness. Qualitative images first; calibrated MPa and AI are not guaranteed outputs.
G09 | Loaded tests | Before applying controlled force | Use rated fixture/grips and appropriate force measurement. Core specimen holder and stepper do not apply or measure tensile load.

## Supplier searches
ID | Item | Status | ElectronicsComp | Robocraze | Quartz Components | FlyRobo | Evelta
B01 | Arduino Uno R3 ATmega328P | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B02 | A4988 carrier with heatsink | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B03 | NEMA17 4-wire bipolar stepper; 17HS4401 candidate | VERIFY DATASHEET | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B04 | UVC USB camera; Logitech C270 candidate only | HOLD: COMPATIBILITY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B05 | Isolated regulated 12 V DC / 3 A enclosed adapter | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B06 | FQP30N06L logic-level N-channel MOSFET | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B07 | SPDT lever microswitch; Omron SS-5GL candidate | VERIFY MOUNT | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B08 | Visible linear polarizing film (P1 and P2) | HOLD: CUT LAYOUT | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B09 | 12 V diffused white LED backlight panel | VERIFY LISTING | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B10 | Fixed P1 polarizer frame | FABRICATE | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B11 | Custom 80T GT2 annular analyzer ring AND P2 holder | HOLD: DRAWING | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B12 | GT2 closed-loop timing belt | HOLD: LENGTH | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B13 | GT2 20T motor pulley | VERIFY SHAFT | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B14 | Bearing / roller support for analyzer ring | HOLD: DRAWING | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B15 | NEMA17 adjustable mounting bracket | VERIFY LAYOUT | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B16 | Home-switch bracket and ring actuator/cam | FABRICATE | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B17 | Rigid adjustable camera mount | VERIFY CAMERA | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B18 | Specimen holder with two gentle edge supports | FABRICATE | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B19 | Backlight/diffuser support | FABRICATE / BUNDLE | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B20 | Rigid optical base / rail | HOLD: LAYOUT | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B21 | M3/M4 fasteners, washers, standoffs | VERIFY LAYOUT | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B22 | 10 kΩ 1/4 W 1% metal-film resistor | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B23 | 4.7 kΩ 1/4 W 1% metal-film resistor | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B24 | 100 Ω 1/4 W 1% metal-film resistor | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B25 | 100 µF 35 V radial electrolytic capacitor | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B26 | 100 nF / 0.1 µF 50 V X7R ceramic capacitor | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B27 | SPST DC power switch | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B28 | Inline fuse holder | VERIFY FUSE | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B29 | 2 A fuse | VERIFY INRUSH | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B30 | Female DC barrel jack to screw terminal | CONDITIONAL PURCHASE | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B31 | 2-position screw terminal blocks | LAYOUT CHOICE | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B32 | Signal wiring / Arduino jumper pigtail harness | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B33 | Power wiring | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B34 | Solderable perfboard | VERIFY LAYOUT | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B35 | A4988 carrier pin headers and mating sockets | CHECK BUNDLE | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B36 | Heat-shrink insulation and cable restraints | SPEC READY | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B37 | Uno USB DATA cable | CHECK BUNDLE | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified
B38 | Clear uncoloured solid polycarbonate coupon | VERIFY MATERIAL | Search — not verified | Search — not verified | Search — not verified | Search — not verified | Search — not verified

## Actual quotes
ID | Component | Order quantity (enter 0 if owned/included) | Actual unit price INR (enter 0 for zero quantity) | Line total INR | Supplier / fabrication shop | Actual product URL / quotation reference | Checked specification / gate / date
B01 | Arduino Uno R3 ATmega328P | [5 empty] | SPEC READY
B02 | A4988 carrier with heatsink | [5 empty] | SPEC READY
B03 | NEMA17 4-wire bipolar stepper; 17HS4401 candidate | [5 empty] | VERIFY DATASHEET
B04 | UVC USB camera; Logitech C270 candidate only | [5 empty] | HOLD: COMPATIBILITY
B05 | Isolated regulated 12 V DC / 3 A enclosed adapter | [5 empty] | SPEC READY
B06 | FQP30N06L logic-level N-channel MOSFET | [5 empty] | SPEC READY
B07 | SPDT lever microswitch; Omron SS-5GL candidate | [5 empty] | VERIFY MOUNT
B08 | Visible linear polarizing film (P1 and P2) | [5 empty] | HOLD: CUT LAYOUT
B09 | 12 V diffused white LED backlight panel | [5 empty] | VERIFY LISTING
B10 | Fixed P1 polarizer frame | [5 empty] | FABRICATE
B11 | Custom 80T GT2 annular analyzer ring AND P2 holder | [5 empty] | HOLD: DRAWING
B12 | GT2 closed-loop timing belt | [5 empty] | HOLD: LENGTH
B13 | GT2 20T motor pulley | [5 empty] | VERIFY SHAFT
B14 | Bearing / roller support for analyzer ring | [5 empty] | HOLD: DRAWING
B15 | NEMA17 adjustable mounting bracket | [5 empty] | VERIFY LAYOUT
B16 | Home-switch bracket and ring actuator/cam | [5 empty] | FABRICATE
B17 | Rigid adjustable camera mount | [5 empty] | VERIFY CAMERA
B18 | Specimen holder with two gentle edge supports | [5 empty] | FABRICATE
B19 | Backlight/diffuser support | [5 empty] | FABRICATE / BUNDLE
B20 | Rigid optical base / rail | [5 empty] | HOLD: LAYOUT
B21 | M3/M4 fasteners, washers, standoffs | [5 empty] | VERIFY LAYOUT
B22 | 10 kΩ 1/4 W 1% metal-film resistor | [5 empty] | SPEC READY
B23 | 4.7 kΩ 1/4 W 1% metal-film resistor | [5 empty] | SPEC READY
B24 | 100 Ω 1/4 W 1% metal-film resistor | [5 empty] | SPEC READY
B25 | 100 µF 35 V radial electrolytic capacitor | [5 empty] | SPEC READY
B26 | 100 nF / 0.1 µF 50 V X7R ceramic capacitor | [5 empty] | SPEC READY
B27 | SPST DC power switch | [5 empty] | SPEC READY
B28 | Inline fuse holder | [5 empty] | VERIFY FUSE
B29 | 2 A fuse | [5 empty] | VERIFY INRUSH
B30 | Female DC barrel jack to screw terminal | [5 empty] | CONDITIONAL PURCHASE
B31 | 2-position screw terminal blocks | [5 empty] | LAYOUT CHOICE
B32 | Signal wiring / Arduino jumper pigtail harness | [5 empty] | SPEC READY
B33 | Power wiring | [5 empty] | SPEC READY
B34 | Solderable perfboard | [5 empty] | VERIFY LAYOUT
B35 | A4988 carrier pin headers and mating sockets | [5 empty] | CHECK BUNDLE
B36 | Heat-shrink insulation and cable restraints | [5 empty] | SPEC READY
B37 | Uno USB DATA cable | [5 empty] | CHECK BUNDLE
B38 | Clear uncoloured solid polycarbonate coupon | [5 empty] | VERIFY MATERIAL
All core purchase decisions entered — item subtotal
Additional tax not already included: enter verified amount or 0
Shipping / delivery: enter verified amount or 0
VERIFIED-INPUT TOTAL (no automatic price verification)
Optional modules are excluded. If purchasing them, add their actual item costs and quantities before treating this as your full order total. Spares/pack quantities can be included in actual order quantities. No estimates prefilled.